## Project Backlog
Project | Employee Management System
Stackholders/ Customers/ Users | Satyam Sir, Employees
Created By | Product Owner
Epic | User Story Id | Feature/Title | User Story | Status | Acceptance criteria
Create an employee management system to create new departments and employees and add those employees to the departments | EMS001 | Existing employee can login into the system | As a previously registered employee, I must be able to login in to the system using my credentials | New | Able to login in the employee if the correct credentials are provided
| EMS002 | New employee can register in the system | As a first time visitor to this system, I must be able to create a new employee record for myself | New | Able to create a new user by creating a new user record in the database and prevent duplicates
| EMS003 | Dashboard Creation for a new employee | As a new user, when I first register in to the system, a dashboard with all my personal data must be created | New | Able to create a dashboard with all the details after the employee registration is completed
| EMS004 | Logged in user see their dashboard | As an employee after logging in to the system, I must be able to see all the details about me in the dashboard | New | Able to display the details of the employee in a good UI after the employee is logged in successfully
| EMS005 | Update the details of a registered Employee | As a registered employee, I must be able to edit all the details about me in the system | New | Able to update the information in the database if the employee requests a change
| EMS006 | Delete the details of a registered Employee | As the employer, I must be able to delete all the details about an employee in the system if he/she resigns the job | New | Able to delete the details of the registered employee from the database and clear the dashboard data
| EMS007 | Employer must be able to have departments | As the employer, I must be able to have all the departments with the respective employees in the system | New | Able to have the ability to add, update or delete employees from departments
| EMS008 | Employer must be able to create new Departments | As the employer, I must be able to create a new department in the system | New | Able to create a department with the ability to add, update or delete employees from it
| EMS009 | Employer must be able to add an employee to departments | As the employer, I must be able to add new employees in the list of departments I had created in the system | New | Able to include an employee who is available in the database under any department
| EMS010 | Employer must be able to update employee in departments | As the employer, I must be able to update the employees in the list of departments in the system | New | Able to update an employee who is available in the database under any department
| EMS011 | Employer must be able to delete an employee from departments | As the employer, I must be able to delete an employee from the list of departments in the system | New | Able to delete an employee who is available in the database from any department

## Sprint Planning
Project | Employee Management System
Stackholders/ Customers/ Users | Satyam Sir, Employees
Created By | Product Owner
Epic | User Story Id | Feature/Title | User Story | Story Points | Sprint
Create an employee management system to create new departments and employees and add those employees to the departments | EMS001 | Existing employee can login into the system | As a previously registered employee, I must be able to login in to the system using my credentials | 8 | 2
| EMS002 | New employee can register in the system | As a first time visitor to this system, I must be able to create a new employee record for myself | 8 | 2
| EMS003 | Dashboard Creation for a new employee | As a new user, when I first register in to the system, a dashboard with all my personal data must be created | 5 | 1
| EMS004 | Logged in user see their dashboard | As an employee after logging in to the system, I must be able to see all the details about me in the dashboard | 3 | 1
| EMS005 | Update the details of a registered Employee | As a registered employee, I must be able to edit all the details about me in the system | 5 | 2
| EMS006 | Delete the details of a registered Employee | As the employer, I must be able to delete all the details about an employee in the system if he/she resigns the job | 3 | 1
| EMS007 | Employer must be able to have departments | As the employer, I must be able to have all the departments with the respective employees in the system | 8 | 2
| EMS008 | Employer must be able to create new Departments | As the employer, I must be able to create a new department in the system | 5 | 1
| EMS009 | Employer must be able to add an employee to departments | As the employer, I must be able to add new employees in the list of departments I had created in the system | 3 | 1
| EMS010 | Employer must be able to update employee in departments | As the employer, I must be able to update the employees in the list of departments in the system | 3 | 1
| EMS011 | Employer must be able to delete an employee from departments | As the employer, I must be able to delete an employee from the list of departments in the system | 2 | 1

## Tasks
QA | Developers
Reviewing User stories | Reviewing User stories
Creating Test Cases | Setting up the Development Environment
Reviewing Test Cases | Assess testability
Setting up the Testing Environment | Designing the Programs
Creating Test Data | Review the Code
Executing Manual Tests | Creating Unit Test Cases
Automation Setup | Excuting Unit Tests
Automation Design | Merging Code
Automating Test Cases | Creating the final builds for deployment
Retesting the Bugs | Fixing Bugs
Regression Testing
Provide the demo of the user story